INSTRUCTED IN WRITING

# Variation order

Get the instruction in writing before the work is done. The JCT and NEC families expect an instruction in writing; a verbal one is confirmed in writing the same day, and the confirmation is kept with this order.

| Field | Entry |
| --- | --- |
| Variation number |  |
| Project |  |
| Contract reference |  |
| Client or main contractor |  |
| Date raised |  |
| Instructed by, name and role |  |
| Instructed on |  |
| How: letter, email, site instruction, verbal |  |
| Their reference |  |
| The change: what is added, omitted or altered, against the drawing, specification or order it changes |  |
| Reason: client request, design change, unforeseen site condition, statutory requirement, error or omission, other |  |
| Cost basis: quoted lump sum, measured at contract rates, daywork priced after, or to be agreed |  |
| Estimated cost, £ |  |
| Agreed value, £ |  |
| Daywork sheet numbers |  |
| Extension sought, days |  |
| Activities and dates affected |  |
| For the contractor: name, signature, date |  |
| For the client: name, signature, date |  |

GUIDANCE

# Getting paid for the variation

Before: an instruction in writing, or a verbal instruction confirmed in writing the same day, with the confirmation kept. During: a daywork sheet signed each day, photographs, and the materials and plant tickets. After: the variation is a line in the next application for payment, with the sum and the basis of calculation.

The payment mechanism is how a variation gets paid. The application states the sum the contractor considers due at the due date and the basis on which it is calculated (Housing Grants, Construction and Regeneration Act 1996, section 110A). A variation that is not in the application is not in the notified sum. If the payer disagrees, the Act gives them one route: a pay less notice before the deadline, stating the sum they consider due and the basis for it. Without one, the notified sum is payable on the final date for payment.

Not legal advice. Check it against GOV.UK and your own contracts and policies.